## Sheet1
Group Member | Task | Hours Spent | Sprint
Matthew Allum
Aaron Muligan
Group Member | Task | Hours Spent | Sprint | Total Hours | Overall Total Hours
[5 empty] | Aaron | 155.5
Matthew Allum | ~ | 6 | 1 | 6 | Lee | 92
Aaron Muligan | ~ | 6 | 1 | 6 | Matt | 166.25
Group Member | Task | Hours Spent | Sprint | Total Hours
2
Matthew Allum | ~ | 6 |  | 6
Aaron Muligan | ~ | 6 |  | 6
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 3 | 5.3
Matthew Allum | Model the notice board | 30 minutes
| Create the animation of falling down the stairs | 5 hours
I want to create at least 5 low poly models for general furniture used in game
Aaron Mulligan | Create the 5 images which will be the puzzle memories | 2 hours |  | 6
| Create the doctors letter which tells you of the MC's condition | 1 hour
| Create the 5 memory post it notes. | 2 hours
| Designing the Notice Board | 1 hours
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 4 | 9
Matthew Allum | As a user, I want to see the house layout ingame | 1 hour
| As a designer, I want to set the positions of the player in the 6 scenes | 5 hour
| As a coder, I want to change the furniture code to spawn specific items only later on in the game | 1 hour
| Create the presentation and practice | 2 hours
Aaron Mulligan | Create the presentation and practice | 2 hours |  | 8
| Finalize the objects to go in specific rooms | 1 hour
| As a designer, I want to create a design document based on the puzzle mechanic | 2 hours
| As a designer, I want to design a management mechanic in the form of a fuse box | 3 hours
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 5 | 6
Matthew Allum | Make the fuse box timer turn off the lights | 1
| Create the fuse box mechanic | 5
Create blog update on the group project
Aaron Mulligan |  |  |  | 6
Create blog update on the group project
Create the puzzle tiling mechanic
| Change the anniversary picture | 1
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 6 | 7
Matthew Allum | Start on the code controlling the carer | 3
| Create blog update on the group project | 1
| Texture Memory Items | 3
Aaron Mulligan | Complete the Puzzle mechanic | 9 |  | 10
| Create blog update on the group project | 1
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 7 | 6.5
Matthew Allum | As designers, I want to update the blog | 0.5
| As a designer, I want to make the player black out when the furniture's relapse time reaches 0 | 2
| As a user, I want to be able to access the upper layer of the house | 2
| As a coder, I need to fix bugs for the fuse box | 1
| As a user, I want to see animations for the blackout event | 1
Aaron Mulligan |  |  |  | 6.5
| As a designer, I want to create the traits of The Carer | 3
| As designers, I want to update the blog | 0.5
| As a modeller, I want to fix the house | 1
| As a user, I want to see the tiling puzzle ingame | 2
Lee Hatchman |  |  |  | 6
| As a new group member, I want to research the material for the brief | 3
| As a new group member, I want to research our two rival games | 2
| As designers, I want to update the blog | 1
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 8 | 7
Matthew Allum | As a designer, I want to create prefabs out of the significant items #58 | 1
| As a user, I want to see how long it takes for the timers to take effect ingame #59 | 1
| As a user, I want to see doors and a railing for the upper level of the game #62 | 3
| As a user, I want to see the difference between the Prologue and Memory 1 #66 | 2
As a group, we need to update our blog on tasks we completed #70
Aaron Mulligan | As a user, I want to see the significant items more clearly#64 | 1 |  | 8
| We need to sort out the project files in Unity #57 | 0.5
| As a designer, I want to fix the camera being moved during puzzles + animations #67 | 2
| As a user, I want to see the prologue and memory 1 work properly #63 | 2
| As a group, we need to update our blog on tasks we completed #70 | 0.5
| As a coder, I want to fix the cursor not appearing on screen correctly #68 | 2
Lee Hatchman | As a user, I want to see coins more clearly ingame via particles or light #65 | 1 |  | 7
| As a modeller, I want to create models of the coins #60 | 1
| As a modeler, I want to see some furniture in the game #61 | 4
| As a group, we need to update our blog on tasks we completed #70 | 1
Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  | 9 | 5.5
Matthew Allum | As a group, we need to update our blogs | 1
As a modeler, I need to start creating the carer
| As a designer, I want the player to approach the carer in memory 2 | 4
| As a user, I want the air to feel more dusty to show how messy the place is in earlier memories | 0.5
Aaron Mulligan | As a group, we need to update our blogs | 1 |  | 7
| As a user, I want to know how mechanics work ingame via instructions | 3
| As a coder, I want to replace the cursor with a reticule to point ingame | 0
| As a designer, I want to make the sliding puzzles for each memory the appropriate picture and difficulty | 2
| As a user, I want to see the difference between the coins ingame | 1
Lee Hatchman | As a group, we need to update our blogs | 1 |  | 5
| As a designer, I want to create 3 initial designs for the UI | 1
| As a modeler, I want to create a long dining table | 0
| As a modeler, I want to create a kitchen counter | 3
Group Member | Task : CHRISTMAS PERIOD | Hours Spent | Sprint | Total Hours
|  |  | 10 | 14
Matthew Allum | ReDo Uvs of the house | 7
| Texture the House Model | 7
Aaron Mulligan | As a designer, change the first memory to something more appropiate | 2 | 10 | 4.5
| As a designer, change the fonts and text on the 5 notes | 2
| As a manager, make sure meeting minutes are up to date and start a new document | 0.5
Lee Hatchman |  |  |  | 6
Group Member | Task : CHRISTMAS PERIOD | Hours Spent | Sprint | Total Hours
|  |  | 11 | 7.5
Matthew Allum | As a modeler, create skirting board around the interior of the house | 6
| As a modeler, create floor frame between rooms to separate them | 0.5
| As a group, we need to update our blogs | 1
| As a modeler, model a window and texture | -
Aaron Mulligan | As a group, we need to update our blogs | 1 |  | 9.5
| As a modeler, model and texture a coffee table | 2
| As a designer, create the letter for the fifth memory | 2
| As a designer, create a template for the doctor letter | 1
| As a designer, create a handwritten letter directed to the MC from a family member | 3.5
Lee Hatchman | As a group, we need to update our blogs | 1 |  | 7
| As a modeler, model and texture shelves | 1
| As a modeler, create and texture a dining table | 2
| As a modeler, model and texture a cabinet | 3
Group Member |  | Hours Spent | Sprint | Total Hours
|  |  | 12 | 10.5
Matthew Allum | As a user, I want to see the updated house in each scene | 0.5
| As a user, I want to see only one memory object in each room | 0.25
| As a designer, I want to create a crosshair ingame | 0.25
| As a group, we need to update our blogs | 1
| As a modeler, model a fridge | 2
| As a modeler, model the cooker | 2
| As a modeler, model and texture a rug | 1.5
| As a group, we need to create the presentation | 1
| As a modeler, texture the fuse box | 2
Aaron Mulligan | Tidy the group folder | 0.5 |  | 11.5
| As a group, we need to update our blogs | 1
| As a designer, place all documents onto the noticeboard | 1
| As a designer, create the doctor notes for each level about the MC condition | 5
| As the coder, make the sliding box puzzle randomize tile pieces straight away | 3
| As a group, we need to create the presentation | 1
Lee Hatchman | As a modeler, retexture the noticeboard | 0.5 |  | 10.5
| As a group, we need to update our blogs | 2
| As a modeler, model and texture a bed side table | 2
| As a modeler, retexture the bookcase | 2
| As a modeler, retexture the dressing mirror | 1
| As a modeler, retexture the grandfather clock | 1
| As a group, we need to create the presentation | 0.5
| As a modeler, retexture the two chair types | 1.5
13-15
| Hours done here |  |  | 9
9
9
Group Member |  | Hours Spent | Sprint | Total Hours
15/2/17 - 22/2/17 |  |  | 16 | 11
Matthew Allum | As a coder, make the carer more aware of where the player is through the level | 4
| As a group, create a blog post on tasks this week | 1
| As a modeler, create 1 models from the furniture list | 3
| As a modeler, texture 1 models from the furniture list | 3
Aaron Mulligan | As a designer, create a list of all sounds needed for our game | 1.5 |  | 7.5
| As a group, create a blog post on tasks this week | 1
| As a coder, replace the box coin prefabs with the coin model | 1
| As a coder, change significant items to puzzle boxes | 1
| As a coder, create start and instructions menu | 2
| As a designer, create game instructions for what the player needs to do | 1
Lee Hatchman | As a modeler, model 3 more furniture items | 3 |  | 7
| As a group, create a blog post on tasks this week | 1
| As a modeler, texture 3 models from the furniture list | 3
Group Member |  | Hours Spent | Sprint | Total Hours
22/2/17 - 1/3/17 |  |  | 17 | 7.75
Matthew Allum
| As a manager, update the sprint hours | 0.25
| As a modeler, texture the stairs | 2
| As a coder, make it so coins change to match their determined coin type | 1.5
| As a modeler, create and texture a furniture model for the house | 2
| As a group, make a blog post update about the game | 1
| As a coder, fix the bug where when the fuse box is cranked completely turning off the lights will break the fuse box | 1
Aaron Mulligan | As a animator, create the carer walking animation using the Mixamo | 2 |  | 6.5
| As a coder, find a way for the player to see the environment when the lights are out | 0.25
| As a coder, test different ideas for the player collider | 2
| As a coder, make the handle for the fuse box rotate when clicked | 0.25
| As a group, make a blog post update about the game | 1
| As a designer, change the coin prefabs with the later art style | 0.5
| As a coder, fix coins falling through the floor | 0.5
Lee Hatchman | As a modeler, texture 3 models for the living room | 3 |  | 7
| As a group, make a blog post update about the game | 0.5
| As a modeler, create 3 furniture models for the living room | 3
| As a modeler, retexture the coin models | 0.5
Group Member |  | Hours Spent | Sprint | Total Hours
1/3/17 - 8/3/17 |  |  | 18 | 5.5
Matthew Allum | As a modeler, create and texture the 5 items listed in the comments below | 5
| As a coder, replace the carer ingame with the animated prefab version with fixes | 0.5
Aaron Mulligan | As a group member, have someone playtest the game | 0.5 |  | 6
| As a coder, look over the prompts ingame and fix any that show when players are not looking at the items | 0.5
| As a sound designer, create a night time looping ambience | 1
| as a sound designer, create a sound that will play when players complete the puzzle box | 0.5
| as a sound designer, create a sound for when the lights go out and come back on | 1.5
| as a sound designer, create a sound for when the player cranks the fuse box | 1
| as a sound designer, create a sound for the fuse box to play to help players find the fuse box in the house | 1
Lee Hatchman | As a modeler, model and texture a standing coat hanger | 2 |  | 6
| As a modeler, model and texture a candle with holder | 2
| As a modeler, model and texture a microwave | 2
Group Member |  | Hours Spent | Sprint | Total Hours
8/3/17 - 15/3/17 |  |  | 19 | 11
Matthew Allum | As a coder, fix the coins spawning on one another | 1
| As a member, import all models into Unity | 4
| As a member, update Scene 1 to how Scene 2 is like | 3
| As a coder, make the player reset if the carer collides with them | 0.5
| As a modeler, model and texture temporary blinds for the windows | 0
| As a group, update our blogs | 1
| As a group, we need to get strangers to playtest our game | 1.5
Aaron Mulligan | As a coder, fix the carer model animation warping backwards when animation finishes | 4 |  | 10.5
| As a designer, create sound for picking up coins | 0.5
| As a designer, create sound for when the player insterts a coin into the fuse box | 0.5
| As a designer, create sound for when the player cranks the emergency switch | 0.5
| As a designer, create sound prompt to help guide the player towards the fuse box | 1
| As a designer, create sound prompt for when the power is almost out | 0.5
| As a designer, create sound for when the fuse box powers up or down | 0.5
| As a designer, change the particle effect for the coins | 0.5
| As a group, update our blogs | 1
| As a group, we need to get strangers to playtest our game | 1.5
Lee Hatchman | As a modeler, retexture the fuse box | 0 |  | 6.5
| As a modeler, model and texture a breaker switch | 2
| As a modeler, model and texture 3 medicine bottles | 2
| As a group, update our blogs | 1
| As a group, we need to get strangers to playtest our game | 1.5
Group Member |  | Hours Spent | Sprint | Total Hours
15/3/17 - 22/3/17 |  |  | 20 | 8.6
Matthew Allum | As a designer, fix the missing art on particular furniture models | 0
| As a designer, make the lighting for the game dynamic (see Github comments) | 5
| As a designer, edit the coin values to allow the player more time when cranked in the fuse box | 0.1
| As a designer, make the rooms lighter when the lights go out | 2
| As a modeler, retexture the fuse box | 1.5
As a modeler, model and texture some temporary blinds for the windows
As a group, make a blog post
Aaron Mulligan | As a designer, fix the text prompt when you go up to the fuse box with a coin | 0.5 |  | 9.5
| As a designer, redesign the noticeboard (see Github comments) | 0
| As a designer, replace memory 1 image with something more fitting | 0.5
| As a sound artist, create or find music piece for the music player to play | 1
| As a sound artist, create sound for when players fall down the stairs | 1
| As a designer, make the coin particles stand out more | 0.5
| As a coder, fix the carer model animation warpng backwards when the animation finishes | 5
| As a group, make a blog post | 1
Lee Hatchman | As a modeler, model and texture ceiling lights | 2 |  | 4
| As a modeler, model and texture doors | 1
| As a group, make a blog post | 1
Group Member |  | Hours Spent | Sprint | Total Hours
22/3/17 - 29/3/17 |  |  | 21 | 10.1
Matthew Allum | As a group, make a blog post
| As a coder, fix the cursor not showing on the puzzle box | 0.1
| As a user, I want to see dynamic lighting in game | 6
| Bug fixes, Animation fixes, Play testing | 4
Aaron Mulligan | As a group, make a blog post | 1 |  | 6.5
| As a group, create a presentation | 1
| As a designer, fix the coin colliders and particle effects | 0.5
| As a designer, redesign the noticeboard | 4
Lee Hatchman | As a group, make a blog post | 1 |  | 5.5
| As a group, create a presentation | 1
| As a designer, fix the missing art on particular furniture models | 1
| As a modeler, model and texture temporary blinds for the windows | 2.5
Group Member |  | Hours Spent | Sprint | Total Hours
29/3/17 - 19/4/17 |  |  | 22 | 13
Matthew Allum | As a coder, make a variable which the game will update to see how many puzzle boards the player must do | 1
| As a coder, make the player turn to the carer when she catches you | 1
| As a sound artist, find sobbing sound effect for the player | 1
| As a user, update objects ingame | 2
| As a coder, implement a short sprint players can do | 2
| As a group, have some people playtest | 0
As a modeler, texture the carer
| As a modeler, look into potentially using Substance Painter 2 | 0.5
| As a group, update our blogs | 0.5
| Other Tasks | 3
| As a designer, fix the flickering dynamic lights | 2
Aaron Mulligan | As a designer, find another cup image and a image of a vinyl record for the puzzle box | 1 |  | 11
| As a designer, figure out a way for the player to know a technique to solving the puzzle box | 1.5
| As a sound artist, find sobbing sound effect for the player | 0
| As a designer, create notes telling the player what the puzzle board looks like | 2
| As a group, have some people playtest | 0.5
As a sound artist, find some ambient sound effects for when the carer is cleaning the house
| As a designer, create some dialogue lines for the carer | 1
| As a designer, look into getting a voice actor for the carer | 0.5
| As a designer, fix the main menu icons going small in full screen | 1
| As a coder, fix the puzzle box squares hiding the text prompt | 0.5
| As a group, update our blogs | 1
| As a group member, fix problems/tidy work | 2
Lee Hatchman | As a modeler, texture the cooker | 2 |  | 5.5
| As a group, update our blogs | 0.5
| As a modeler, look into potentially using Substance Painter 2 | 0.5
| As a group, have some people playtest | 0.5
| As a modeler, texture the record player | 2