## Sheet1
level-6-l6-group-1 | Group Member | Task | Hours Spent | Sprint
Matthew Allum
Aaron Muligan
| Group Member | Task | Hours Spent | Sprint | Total Hours | Overall Total Hours
| Matthew Allum | ~ | 6 | 1 | 6
| Aaron Muligan | ~ | 6 | 1 | 6
| Group Member | Task | Hours Spent | Sprint | Total Hours
2
| Matthew Allum | ~ | 6 |  | 6
| Aaron Muligan | ~ | 6 |  | 6
| Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  |  | 3 | 5.3
| Matthew Allum | Model the notice board | 30 minutes |  | 5
|  | Create the animation of falling down the stairs | 5 hours
I want to create at least 5 low poly models for general furniture used in game
| Aaron Mulligan | Create the 5 images which will be the puzzle memories | 2 hours
Create the doctors letter which tells you of the MC's condition
|  | Create the 5 memory post it notes. | 2 hours
|  | Designing the Notice Board | 1 hours
| Group Member | Task | Hours Spent | Sprint | Total Hours
|  |  |  | 4 | 9
| Matthew Allum | As a user, I want to see the house layout ingame | 1 hour
|  | As a designer, I want to set the positions of the player in the 6 scenes | 5 hour
|  | As a coder, I want to change the furniture code to spawn specific items only later on in the game | 1 hour
|  | Create the presentation and practice | 2 hours
| Aaron Mulligan | Create the presentation and practice
Finalize the objects to go in specific rooms
As a designer, I want to create a design document based on the puzzle mechanic
As a designer, I want to design a management mechanic in the form of a fuse box
| Group Member | Task | Hours Spent | Sprint | Total Hours
4
| Matthew Allum | Make the fuse box timer turn off the lights | 1
|  | Create the fuse box mechanic | 5
Create blog update on the group project
Aaron Mulligan
Create blog update on the group project
Create the puzzle tiling mechanic
Change the anniversary picture